## Dashboard
Team 2 Budget Dashboard
Only fill Daily Timesheet. Other sheets update from it.
Planned Total Hours | 864 | Sprint Review Talking Points
Actual Total Hours | 494.5 | 1. Planned vs actual hours for the current sprint.
Remaining Hours | 26235 | 2. Budget tasks currently marked Watch or Over Plan.
Planned Total Cost |  | 3. Cause of any variance and the mitigation decision.
Actual Total Cost | 14835 | 4. Whether any P1 features should be de-scoped to protect P0 delivery.
Remaining Budget | 11400
Budget Status | On Track
Unmapped Hours | 36
Unmapped Cost | 1080

## Daily Timesheet
Date | Sprint | Role | Budget Task | Activity | Hours | Service Cost | Actual Cost | Status | Notes / Evidence
2026-05-19 | Intro | Product & UX Lead | 1. Product discovery, interviews & persona synthesis | Research | 5 | 0 | 150 | Done | do some interviews, define user personas (Exec, Foodie, Restauranteur, Explorer)
2026-05-21 | Intro | Product & UX Lead | 3. Competitive analysis & business plan refinement | Documentation | 5 | 0 | 150 | Done | create a business plan with budget time sheet
2026-05-24 | Sprint 1 | Web Frontend Lead | 2. Requirements, user stories & backlog management | Research | 1 | 0 | 30 | Done | Research different development tools and JavaScript libraries
2026-05-25 | Sprint 1 | Web Frontend Lead | 2. Requirements, user stories & backlog management | Research | 2 | 0 | 60 | Done | Research and download needed infrastructure for coding (extensions, programs, etc.)
2026-05-25 | Sprint 1 | Mobile App Lead | 2. Requirements, user stories & backlog management | Research | 5 | 0 | 150 | Done | Investigating best practice mobile devlopment frameworks with a focus on multi-platform support (iOS and Android)
2026-05-25 | Sprint 1 | Data & ML Lead | 5. Dataset acquisition, EDA & data-quality checks | Research | 2 | 0 | 60 | Done | api research
2026-05-26 | Sprint 1 | Product & UX Lead | 2. Requirements, user stories & backlog management | Requirements | 4 | 0 | 120 | Done | create user stories with ac; set mvp features and nice-to-have features
2026-05-26 | Sprint 1 | Mobile App Lead | 4. UX flows, wireframes & Google Stitch prototype | Research | 3 | 0 | 90 | Done | exploration of the chosen mobile framework: React Native, NativeWind, and expo. First steps: set-up documentation and development environment
2026-05-26 | Sprint 1 | Data & ML Lead | 5. Dataset acquisition, EDA & data-quality checks | Data/ML | 2 | 0 | 60 | Done | data availablity check
2026-05-28 | Sprint 1 | Backend Lead | 8. Backend API gateway, booking and offer services | Development | 4 | 0 | 120 | Done | bootstrapped the API gateway and health endpoint.
2026-05-29 | Sprint 1 | Mobile App Lead | 4. UX flows, wireframes & Google Stitch prototype | UX/UI Design | 4 | 0 | 120 | Done | Creation of Mobile UI mockups + Page descriptions
2026-05-30 | Sprint 1 | Data & ML Lead | 5. Dataset acquisition, EDA & data-quality checks | Data/ML | 2 | 0 | 60 | In Progress | data quality check
2026-06-02 | Sprint 1 | Web Frontend Lead | 2. Requirements, user stories & backlog management | Requirements | 3 | 0 | 90 | Done | Plan out core component structure, begin developing website aesthetics (typeface, color palette, CSS, etc.)
2026-06-02 | Sprint 1 | Mobile App Lead | 4. UX flows, wireframes & Google Stitch prototype | Documentation | 7 | 0 | 210 | Done | Development of page architecture and user flows, preparation of Frontend Strategy and first demo of page view structure
2026-06-02 | Sprint 1 | Backend Lead | 9. PostgreSQL schema and seed data | Development | 5 | 0 | 150 | Done | implemented PostgreSQL schema/migrations and Docker Compose database workflow.
2026-06-02 | Sprint 1 | Backend Lead | 8. Backend API gateway, booking and offer services | Documentation | 3 | 0 | 90 | Done | authored API contract v0 and OpenAPI specification.
2026-06-03 | Sprint 1 | Product & UX Lead | 2. Requirements, user stories & backlog management | Documentation | 3 | 0 | 90 | Done | create backlogs based on user stories
2026-06-03 | Sprint 1 | Mobile App Lead | 11. Mobile app implementation: onboarding and booking | Development | 2 | 0 | 60 | In Progress | Development of a first demo application based off of the Mobile UI mockups and page flow architecture with mock API endpoints
2026-06-03 | Sprint 1 | Backend Lead | 8. Backend API gateway, booking and offer services | Documentation | 4 | 0 | 120 | Done | documented the system architecture decision record.
2026-06-04 | Sprint 1 | Scrum Master & Integration Lead | 2. Requirements, user stories & backlog management | Integration | 10 | 0 | 300 | Done | Planned out the integration flow and documented the ADR for the team to have a sturdy reference point.
2026-06-04 | Sprint 1 | Scrum Master & Integration Lead | 12. Restaurant dashboard and campaign workflow | Documentation | 2 | 0 | 60 | Done | Drafted and redrafted contract documentation for the team.
2026-06-04 | Sprint 1 | Backend Lead | 5. Dataset acquisition, EDA & data-quality checks | Documentation | 3 | 0 | 90 | Done | documented Manhattan datasets, busyness strategy and ETL mapping.
2026-06-04 | Sprint 1 | Mobile App Lead | 4. UX flows, wireframes & Google Stitch prototype | Documentation | 2 | 0 | 60 | Done | Added the frontend strategy in documentation, include mobile stack + component conventions
2026-06-05 | Sprint 1 | Mobile App Lead | 11. Mobile app implementation: onboarding and booking | Development | 4 | 0 | 120 | Done | Initial scaffolding of the mobile application
2026-06-08 | Sprint 2 | Product & UX Lead | 3. Competitive analysis & business plan refinement | Documentation | 0.5 | 0 | 15 | Done | update bussiness plan with standard gantt chart
2026-06-08 | Sprint 2 | Product & UX Lead | 2. Requirements, user stories & backlog management | Requirements | 1.5 | 0 | 45 | Done | Based on the interviews and personas, generate more realistic user stories mapping with AC.
2026-06-08 | Sprint 2 | Backend Lead | 9. PostgreSQL schema, seed data and Redis cache | Development | 5 | 0 | 150 | Done | added deterministic demo seed data and seed workflow.
2026-06-08 | Sprint 2 | Backend Lead | 8. Backend API gateway, booking and offer services | Documentation | 1 | 0 | 30 | Done | aligned ADR artifacts with the implemented architecture.
2026-06-09 | Sprint 2 | Product & UX Lead | 4. UX flows, wireframes & Google Stitch prototype | UX/UI Design | 1.5 | 0 | 45 | Done | create the basic web mockup for c-side using stitch
2026-06-09 | Sprint 2 | Backend Lead | 8. Backend API gateway, booking and offer services | Development | 5 | 0 | 150 | Done | implemented Express middleware, PostgreSQL pool, API routes and readiness endpoint.
2026-06-09 | Sprint 2 | Backend Lead | 9. PostgreSQL schema, seed data and Redis cache | Documentation | 1 | 0 | 30 | Done | improved database setup and schema documentation.
2026-06-09 | Sprint 2 | Data & ML Lead | 5. Dataset acquisition, EDA & data-quality checks | Data/ML | 4 | 0 | 120 | Done | Cleaned and profiled the NYC restaurant inspection dataset; checked missing values, duplicates, coordinate coverage and cuisine distributions.
2026-06-10 | Sprint 2 | Product & UX Lead | 2. Requirements, user stories & backlog management | Research | 1 | 0 | 30 | Done | web-side vs. mobile-side differentiation summary
2026-06-10 | Sprint 2 | Mobile App Lead | 11. Mobile app implementation: onboarding and booking | Research | 2 | 0 | 60 | Done | Research shared state-management solutions for mobile and web (eg. Redux)
2026-06-10 | Sprint 2 | Mobile App Lead | 11. Mobile app implementation: onboarding and booking | Meeting | 1 | 0 | 30 | Done | Weekly standup meeting w/ Frontend lead
2026-06-12 | Sprint 2 | Mobile App Lead | 11. Mobile app implementation: onboarding and booking | Development | 2 | 0 | 60 | Done | Implementation of shared NPM workspace for mobile and web frameworks including workspace entrypoints - support Redux
2026-06-13 | Sprint 2 | Mobile App Lead | 4. UX flows, wireframes & Google Stitch prototype | Requirements | 2 | 0 | 60 | Done | Refinement of the UX flows based on the refined user stories - mobile v. webapp differentiation
2026-06-15 | Sprint 2 | Web Frontend Lead | 10. Web app implementation: discovery, booking, offers | Development | 5 | 0 | 150 | Done | Implemented booking and offers infrastructure for merchants (Add tables/seating, send flash deals)
2026-06-16 | Sprint 2 | Mobile App Lead | 11. Mobile app implementation: onboarding and booking | Development | 4 | 0 | 120 | Done | Development of Redux Toolkit State slice for API access, standard interface for both web and mobile applications
2026-06-16 | Sprint 2 | Scrum Master & Integration Lead | 4. UX flows, wireframes & Google Stitch prototype | Development | 5 | 0 | 150 | Done | Redid the wireframes for the Stitch prototype
2026-06-17 | Sprint 2 | Web Frontend Lead | 2. Requirements, user stories & backlog management | Requirements | 1 | 0 | 30 | Done | Added in options for merchants to toggle if their establishment has accessability features (wheelchair ramps, braile menus, etc.). Also added in options for allergens on the menu
2026-06-17 | Sprint 2 | Mobile App Lead | 11. Mobile app implementation: onboarding and booking | Development | 3 | 0 | 90 | Done | Retooling and resolving issues with shared dependencies to implement NativeWind styling across mobile
2026-06-17 | Sprint 2 | Web Frontend Lead | 6. Data cleaning, feature engineering & merging | Development | 3 | 0 | 90 | Done | Reworked code into Component structure, merged code with Mobile
2026-06-17 | Sprint 2 | Scrum Master & Integration Lead | 12. Restaurant dashboard and campaign workflow | Research | 2 | 0 | 60 | Done | Meeting with Frontend and Mobile Leads to redesign design scope for each domain.
2026-06-17 | Sprint 2 | Data & ML Lead | 6. Data cleaning, feature engineering & merging | Data/ML | 5 | 0 | 150 | Done | Merged restaurant records with PLUTO building attributes and TLC taxi zones; created a restaurant-area proxy and validated spatial joins.
2026-06-17 | Sprint 2 | Mobile App Lead | 11. Mobile app implementation: onboarding and booking | Meeting | 1 | 0 | 30 | Done | Weekly standup meeting w/ Frontend lead
2026-06-18 | Sprint 2 | Mobile App Lead | 11. Mobile app implementation: onboarding and booking | Development | 5 | 0 | 150 | Done | Implement card view, preferences filter, and restaurant views for customers (outstanding is the MapView element --> no compatability with web environment for react-native-mapping)
2026-06-18 | Sprint 2 | Web Frontend Lead | 6. Data cleaning, feature engineering & merging | Deployment | 5 | 0 | 150 | Done | Adding/tweaking features (Aesthetics, Room/table/chair features, Occupancy meters, filters, mapping infrastructure, etc)
2026-06-18 | Sprint 2 | Scrum Master & Integration Lead | 3. Competitive analysis & business plan refinement | Development | 8 | 0 | 240 | Done | Meeting with Product Owner to generate presentations and refine business plan
2026-06-18 | Sprint 2 | Backend Lead | 8. Backend API gateway, booking and offer services | Development | 6 | 0 | 180 | Done | implemented user profile and nearby-restaurant discovery endpoints.
2026-06-19 | Sprint 2 | Mobile App Lead | Else / Unmapped | Development | 2 | 0 | 60 | In Progress | Adding state functions to shared Redux package
2026-06-22 | Sprint 3 | Scrum Master & Integration Lead | 2. Requirements, user stories & backlog management | Documentation | 3 | 0 | 90 | Done | Creation of tasks for Sprint 3 on Jira board.
2026-06-22 | Sprint 3 | Backend Lead | 8. Backend API gateway, booking and offer services | Development | 6 | 0 | 180 | Done | implemented restaurant ETA and booking confirmation endpoints.
2026-06-23 | Sprint 3 | Scrum Master & Integration Lead | 17. Cloud deployment, CI/CD and monitoring | Development | 4 | 0 | 120 | Done | TABL 501,502,503,504 done.
2026-06-23 | Sprint 3 | Mobile App Lead | 10. Web app implementation: discovery, booking, offers | Integration | 4 | 0 | 120 | Done | Integrate Sprint 02 Development work for mobile and frontend, handle dependency issues
2026-06-23 | Sprint 3 | Mobile App Lead | 11. Mobile app implementation: onboarding and booking | Integration | 2 | 0 | 60 | Done | Merge and refactor mobile and frontend code from Sprint 2 final
2026-06-23 | Sprint 3 | Backend Lead | 8. Backend API gateway, booking and offer services | Development | 7 | 0 | 210 | Done | implemented offers inbox, offer acceptance and manager campaigns.
2026-06-24 | Sprint 3 | Scrum Master & Integration Lead | 17. Cloud deployment, CI/CD and monitoring | Development | 6 | 0 | 180 | Done | TABL 613, 612 and 614 sorted out.
2026-06-24 | Sprint 3 | Web Frontend Lead | 6. Data cleaning, feature engineering & merging | Development | 2.5 | 0 | 75 | In Progress | Started Account and Profile setup for Merchants platform
2026-06-24 | Sprint 3 | Web Frontend Lead | 2. Requirements, user stories & backlog management | Requirements | 2 | 0 | 60 | In Progress | Write frontend strategy for integration with backend API
2026-06-24 | Sprint 3 | Backend Lead | 9. PostgreSQL schema, seed data and Redis cache | Development | 2 | 0 | 60 | Done | added restaurant capacity/cuisine migration and serialization.
2026-06-24 | Sprint 3 | Backend Lead | 7. ML / heuristic matching and busyness prediction | Integration | 6 | 0 | 180 | Done | integrated FastAPI campaign matching with distance fallback and offer insertion.
2026-06-24 | Sprint 3 | Data & ML Lead | 6. Data cleaning, feature engineering & merging | Data/ML | 5 | 0 | 150 | Done | Engineered rating, log review count, visit-duration, time, weekend, turnover, takeaway and local taxi-demand features for busyness modelling.
2026-06-24 | Sprint 3 | Mobile App Lead | 11. Mobile app implementation: onboarding and booking | Meeting | 1 | 0 | 30 | Done | Weekly standup meeting w/ Frontend lead
2026-06-25 | Sprint 3 | Product & UX Lead | Else / Unmapped | UX/UI Design | 2 | 0 | 60 | Done | Created a UI-style guide to keep the web + mobile app consistent
2026-06-25 | Sprint 3 | Product & UX Lead | Else / Unmapped | Development | 2 | 0 | 60 | Done | Write froentend code based on the ui style guide for teammates to refer
2026-06-25 | Sprint 3 | Web Frontend Lead | 10. Web app implementation: discovery, booking, offers | Development | 3 | 0 | 90 | Done | Added in final features (booking table, linking booking, occupancy, rooms, etc)
2026-06-25 | Sprint 3 | Backend Lead | 8. Backend API gateway, booking and offer services | Development | 3 | 0 | 90 | Done | added authenticated user booking-history endpoint.
2026-06-25 | Sprint 3 | Mobile App Lead | 11. Mobile app implementation: onboarding and booking | Development | 3 | 0 | 90 | Done | Changed styling to use nativewind + removed redundant files/fixed dir layout
2026-06-26 | Sprint 3 | Mobile App Lead | 10. Web app implementation: discovery, booking, offers | Integration | 2 | 0 | 60 | Done | Fixed integration issues with Frontend app, merged into main
2026-06-27 | Sprint 3 | Backend Lead | 9. PostgreSQL schema, seed data and Redis cache | Data/ML | 7 | 0 | 210 | Done | generated real Manhattan restaurant seed data aligned with ML identifiers.
2026-06-29 | Sprint 3 | Web Frontend Lead | 10. Web app implementation: discovery, booking, offers | Integration | 4 | 0 | 120 | In Progress | Began to integrate databases and put in infrastructure for API keys
2026-06-29 | Sprint 3 | Mobile App Lead | 13. Google Maps ETA and geospatial filtering | Development | 3 | 0 | 90 | Done | Add functionality for checking geospatial filtering compared
2026-06-29 | Sprint 3 | Backend Lead | 13. Google Maps ETA and geospatial filtering | Development | 8 | 0 | 240 | Done | integrated Google Routes ETA with haversine fallback, tests and API contract updates.
2026-06-29 | Sprint 3 | Mobile App Lead | 11. Mobile app implementation: onboarding and booking | Bug Fix | 1 | 0 | 30 | Done | Fixed longstanding SDK version conflict, could not boot on device properly (pinned version across repo)
2026-06-30 | Sprint 3 | Mobile App Lead | 11. Mobile app implementation: onboarding and booking | Integration | 5 | 0 | 150 | Done | Integration of backend api connectivity for user functionality, including onboarding flow and booking flow. Integration of map elements with backnd api from MVP
2026-06-30 | Sprint 3 | Data & ML Lead | 7. ML / heuristic matching and busyness prediction | Data/ML | 6 | 0 | 180 | Done | Built the XGBoost classification pipeline, created train/test splits and compared model performance using accuracy, macro-F1 and class-level recall.
2026-07-01 | Sprint 3 | Web Frontend Lead | Else / Unmapped | Bug Fix | 5 | 0 | 150 | Done | Technical issues while getting Docker/PostgreSQL to work on my computer
2026-07-01 | Sprint 3 | Mobile App Lead | 11. Mobile app implementation: onboarding and booking | Development | 4 | 0 | 120 | Done | Add inbox tab, auth slice, and offer card
2026-07-01 | Sprint 3 | Mobile App Lead | 11. Mobile app implementation: onboarding and booking | Meeting | 1 | 0 | 30 | Done | Weekly standup meeting w/ Frontend lead
2026-07-02 | Sprint 3 | Web Frontend Lead | 10. Web app implementation: discovery, booking, offers | Integration | 6 | 0 | 180 | In Progress | Reworked code to better use Redux, attempted to integrate databases but tables need updating for merchant needs
2026-07-02 | Sprint 3 | Backend Lead | 8. Backend API gateway, booking and offer services | Development | 4 | 0 | 120 | Done | added restaurant booking feed for the merchant dashboard.
2026-07-02 | Sprint 3 | Mobile App Lead | 11. Mobile app implementation: onboarding and booking | Development | 2 | 0 | 60 | Done | Add ETA routing check to the booking system
2026-07-02 | Sprint 3 | Mobile App Lead | 11. Mobile app implementation: onboarding and booking | Development | 2 | 0 | 60 | Done | explore support for push notifications, add a stub entrypoint and update the notification strategy
2026-07-04 | Sprint 3 | Backend Lead | 8. Backend API gateway, booking and offer services | Documentation | 3 | 0 | 90 | Done | aligned architecture docs with JWT, Routes API and REST polling.
2026-07-06 | Sprint 4 | Mobile App Lead | 11. Mobile app implementation: onboarding and booking | Development | 2 | 0 | 60 | Done | Lift existing state management to the redux store, including session location
2026-07-06 | Sprint 4 | Web Frontend Lead | 10. Web app implementation: discovery, booking, offers | Integration | 5 | 0 | 150 | Done | Reworked Frontend code entirely to work with the Backend. Confirmed working
2026-07-06 | Sprint 4 | Backend Lead | 8. Backend API gateway, booking and offer services | Development | 8 | 0 | 240 | Done | implemented JWT register/login/logout, dependencies and auth error handling.
2026-07-07 | Sprint 4 | Product & UX Lead | 15. EDI/accessibility features and usability testing | Testing/QA | 2 | 0 | 60 | Done | Write the Testing SPEC file to make sure that each testing should be safe and effective.
2026-07-08 | Sprint 4 | Web Frontend Lead | 12. Restaurant dashboard and campaign workflow | Development | 3 | 0 | 90 | Done | Added merchant sign-up flow, WCAG AA fixes, live offer tracker, and form validation
2026-07-08 | Sprint 4 | Product & UX Lead | 15. EDI/accessibility features and usability testing | Testing/QA | 3 | 0 | 90 | Done | Unit testing based on the current version -- `integrate branch`
2026-07-08 | Sprint 4 | Product & UX Lead | 15. EDI/accessibility features and usability testing | Testing/QA | 3 | 0 | 90 | Done | Integration testing based on the current version
2026-07-08 | Sprint 4 | Mobile App Lead | 11. Mobile app implementation: onboarding and booking | Meeting | 1 | 0 | 30 | Done | Weekly standup meeting w/ Frontend lead
2026-07-09 | Sprint 4 | Product & UX Lead | 15. EDI/accessibility features and usability testing | Testing/QA | 3 | 0 | 90 | Done | Api contract validation
2026-07-09 | Sprint 4 | Scrum Master & Integration Lead | 17. Cloud deployment, CI/CD and monitoring | Deployment | 3 | 0 | 90 | Done | Staging project Setup
2026-07-09 | Sprint 4 | Backend Lead | 8. Backend API gateway, booking and offer services | Development | 6 | 0 | 180 | Done | implemented and stabilized merchant restaurant creation/settings endpoints.
2026-07-09 | Sprint 4 | Data & ML Lead | 7. ML / heuristic matching and busyness prediction | Data/ML | 4.5 | 0 | 135 | Done | Tuned XGBoost hyperparameters and reviewed the normalized confusion matrix, with particular attention to severe-queue recall and class imbalance.
2026-07-10 | Sprint 4 | Scrum Master & Integration Lead | 17. Cloud deployment, CI/CD and monitoring | Deployment | 3 | 0 | 90 | Done | DB Password & user setup/connection string troubleshooting
2026-07-11 | Sprint 4 | Product & UX Lead | 18. Demo, final paper, presentation and interview prep | Deployment | 2 | 0 | 60 | Done | Start the final paper: introduction, methodology, system architecture (reuse docs/system-architecture-map.md), and evaluation plan.
2026-07-11 | Sprint 4 | Scrum Master & Integration Lead | 17. Cloud deployment, CI/CD and monitoring | Deployment | 3 | 0 | 90 | Done | Cloud Run deploy triggers, api-gateway + ml-service
2026-07-11 | Sprint 4 | Backend Lead | 8. Backend API gateway, booking and offer services | Development | 4 | 0 | 120 | Done | added campaign cancellation and pending-offer revocation.
2026-07-12 | Sprint 4 | Web Frontend Lead | 10. Web app implementation: discovery, booking, offers | Development | 1 | 0 | 30 | Done | Set up password recovery for accounts
2026-07-12 | Sprint 4 | Scrum Master & Integration Lead | 17. Cloud deployment, CI/CD and monitoring | Deployment | 2.5 | 0 | 75 | Done | Firebase Hosting deploy automation + Google Maps key debug
2026-07-12 | Sprint 4 | Mobile App Lead | 13. Google Maps ETA and geospatial filtering | Development | 1.5 | 0 | 45 | Done | Fixed tab routing issues, added geospatial search radius constant, corrected euro price symbol formatting on restaurant cards
2026-07-12 | Sprint 4 | Backend Lead | 9. PostgreSQL schema, seed data and Redis cache | Development | 3 | 0 | 90 | Done | added RevPASH schema fields, view and demo seed.
2026-07-12 | Sprint 4 | Backend Lead | 8. Backend API gateway, booking and offer services | Development | 5 | 0 | 150 | Done | implemented RevPASH API and booking lifecycle actions.
2026-07-12 | Sprint 4 | Backend Lead | 16. Automated tests, integration QA and bug fixing | Testing/QA | 2 | 0 | 60 | Done | expanded Postman smoke journeys and aligned API documentation.
2026-07-13 | Sprint 4 | Web Frontend Lead | 6. Data cleaning, feature engineering & merging | Deployment | 2.5 | 0 | 75 | Done | Fixed Logout bug, tweaked password recovery
2026-07-13 | Sprint 4 | Scrum Master & Integration Lead | 17. Cloud deployment, CI/CD and monitoring | Deployment | 3.5 | 0 | 105 | Done | GCP general debug and resolution
2026-07-13 | Sprint 4 | Mobile App Lead | 11. Mobile app implementation: onboarding and booking | Integration | 5 | 0 | 150 | Done | Wired authentication API end-to-end: login/registration views, auth redirect flow and context refactor. Added neighbourhood selection fallback for users outside coverage area; refined booking flow
2026-07-13 | Sprint 4 | Backend Lead | 8. Backend API gateway, booking and offer services | Development | 7 | 0 | 210 | Done | added password reset flow and campaign capacity validation.
2026-07-14 | Sprint 4 | Mobile App Lead | 11. Mobile app implementation: onboarding and booking | Development | 3 | 0 | 90 | Done | Performance pass (memoized restaurant card generation), fixed profile generation from backend state, UI cleanup; bundled mobile app version 1
2026-07-15 | Sprint 4 | Mobile App Lead | 11. Mobile app implementation: onboarding and booking | Integration | 2.5 | 0 | 75 | Done | Merged integrate branch into mobile deployment branch, moved project ownership to group repo, added logout and guest "continue without login" mode
2026-07-15 | Sprint 4 | Web Frontend Lead | 15. EDI/accessibility features and usability testing | Testing/QA | 2 | 0 | 60 | Done | Testing speed of database updating when campaign is started/accepted, bug hunting, etc
2026-07-15 | Sprint 4 | Mobile App Lead | 11. Mobile app implementation: onboarding and booking | Meeting | 1 | 0 | 30 | Done | Weekly standup meeting w/ Frontend lead
2026-07-16 | Sprint 4 | Mobile App Lead | 15. EDI/accessibility features and usability testing | Development | 2.5 | 0 | 75 | Done | Added settings modal and light mode theme support across the mobile app; polished logout/guest session handling
2026-07-17 | Sprint 4 | Mobile App Lead | 15. EDI/accessibility features and usability testing | Development | 6 | 0 | 180 | Done | User-testing fixes (per docs/user-testing-fixes-strategy.md): new Discover tab with ranked carousels, cuisine photo cards, shared search + busyness filtering, collapsible filters on all views, editable preferences, scrollable profile/bookings, light-theme fixes
2026-07-20 | Sprint 5 | Mobile App Lead | 15. EDI/accessibility features and usability testing | Documentation | 1.5 | 0 | 45 | Done | Wrote user-testing fixes strategy doc (256 lines) translating Sprint 4 User Testing feedback into P0/P1 fixes;
2026-07-20 | Sprint 5 | Mobile App Lead | 11. Mobile app implementation: onboarding and booking | Development | 2 | 0 | 60 | Done | Discover tab (top picks, quiet spots, cuisine browsing) + cuisine photography on restaurant cards, 21 cuisine assets
2026-07-20 | Sprint 5 | Mobile App Lead | 11. Mobile app implementation: onboarding and booking | Development | 1.5 | 0 | 45 | Done | Editable profile preferences (EditPreferencesModal, PreferenceEditor) + expanded bookings section. Refactored onboarding onto shared editor.
2026-07-20 | Sprint 5 | Mobile App Lead | 13. Google Maps ETA and geospatial filtering | Development | 2 | 0 | 60 | Done | UI Improvements: Shared search + busyness filtering across card and map views (restaurantFilters in shared pkg), collapsible filters panel, map top-picks highlighting, scroll-to-top
2026-07-20 | Sprint 5 | Mobile App Lead | 15. EDI/accessibility features and usability testing | UX/UI Design | 1 | 0 | 30 | Done | Auxillary UI improvements: Ionicons refactor replacing emoji icons across bookings/offers/inbox; light-mode contrast fix on settings switches
2026-07-21 | Sprint 5 | Backend Lead | 8. Backend API gateway, booking and offer services | Development | 7 | 0 | 210 | Done | added campaign-offer tracking, neighborhood fallback and API rate limiting.
2026-07-21 | Sprint 5 | Backend Lead | 18. Demo, final paper, presentation and interview prep | Documentation | 1 | 0 | 30 | Done | documented tutor-approved withdrawal of Generative AI from project scope.
2026-07-22 | Sprint 5 | Mobile App Lead | 11. Mobile app implementation: onboarding and booking | Development | 1.5 | 0 | 45 | Done | Lifted mobile constants into frontend/packages/shared as single source of truth across 8 call sites
2026-07-22 | Sprint 5 | Mobile App Lead | 11. Mobile app implementation: onboarding and booking | Bug Fix | 1 | 0 | 30 | Done | Removed redundant legacy routing and dead screens
2026-07-22 | Sprint 5 | Mobile App Lead | 11. Mobile app implementation: onboarding and booking | Development | 1 | 0 | 30 | Done | Add pull to refresh for map and tab view - based on feedback from Scrum Master usage.
2026-07-22 | Sprint 5 | Backend Lead | 8. Backend API gateway, booking and offer services | Bug Fix | 5 | 0 | 150 | Done | enforced one-active-booking, hold expiry and booking-history limits.
2026-07-23 | Sprint 5 | Mobile App Lead | 18. Demo, final paper, presentation and interview prep | Meeting | 0.5 | 0 | 15 | Done | Standup meeting, discussing final demo steps.
2026-07-23 | Sprint 5 | Data & ML Lead | 7. ML / heuristic matching and busyness prediction | Integration | 5 | 0 | 150 | Done | Packaged the fitted preprocessing and XGBoost pipeline as a joblib artifact; verified feature order and predictions against fixed restaurant feature data.
2026-07-24 | Sprint 5 | Product & UX Lead | Else / Unmapped | Testing/QA | 4 | 0 | 120 | Done | Prepare an interview guide and a testing plan for real users.
2026-07-24 | Sprint 5 | Mobile App Lead | 18. Demo, final paper, presentation and interview prep | Meeting | 3 | 0 | 90 | Done | Coordination meeting to discuss current state of application, conducted a code review of various components and identified action areas for the application.
2026-07-24 | Sprint 5 | Backend Lead | 8. Backend API gateway, booking and offer services | Development | 3 | 0 | 90 | Done | added the default 15-minute campaign TTL.
2026-07-25 | Sprint 5 | Product & UX Lead | Else / Unmapped | Testing/QA | 10 | 0 | 300 | Done | Find real users to do the usability test: Participants were asked to complete realistic tasks while describing their expectations, points of hesitation, and interpretation of system feedback.
2026-07-25 | Sprint 5 | Backend Lead | 8. Backend API gateway, booking and offer services | Development | 6 | 0 | 180 | Done | added configurable TTL and hardened legacy authentication/rate limits.
2026-07-26 | Sprint 5 | Product & UX Lead | Else / Unmapped | Documentation | 5 | 0 | 150 | Done | Record users feelings and thoughts, consolidate feeback into a prioritized action list and write a report.
2026-07-26 | Sprint 5 | Mobile App Lead | 11. Mobile app implementation: onboarding and booking | Development | 1 | 0 | 30 | Done | Fixes to the web port of the mobile application, based on some issues identified during user testing of the web port by Product Lead.
2026-07-26 | Sprint 5 | Mobile App Lead | 11. Mobile app implementation: onboarding and booking | Development | 1 | 0 | 30 | Done | Based on Product Lead Testing: Split booking/offer checkout into separate modal components, extracted ModalSheet + EtaNotice, offer booking now validates modal choice, booking copy clarified
2026-07-26 | Sprint 5 | Mobile App Lead | 11. Mobile app implementation: onboarding and booking | Development | 2 | 0 | 60 | Done | Map view rework: draggable bottom pane (DraggableSheet), filter bar converted to overlay (no longer expands other elements)
2026-07-26 | Sprint 5 | Backend Lead | 9. PostgreSQL schema, seed data and Redis cache | Development | 4 | 0 | 120 | Done | moved categorized user preferences into a dedicated table.
2026-07-26 | Sprint 5 | Backend Lead | 5. Dataset acquisition, EDA & data-quality checks | Data/ML | 3 | 0 | 90 | Done | added the historical taxi-demand data table.
2026-07-27 | Sprint 5 | Mobile App Lead | 6. Data cleaning, feature engineering & merging | Bug Fix | 0.5 | 0 | 15 | Done | Write a script to aggregate duplicate restaurant data, used to re-seed the database
2026-07-27 | Sprint 5 | Backend Lead | 9. PostgreSQL schema, seed data and Redis cache | Development | 3 | 0 | 90 | Done | added restaurant rating and review fields.
2026-07-27 | Sprint 5 | Mobile App Lead | 7. ML / heuristic matching and busyness prediction | Testing/QA | 2 | 0 | 60 | Done | write testing for the refactor ml service and heuristic match
2026-07-27 | Sprint 5 | Mobile App Lead | 7. ML / heuristic matching and busyness prediction | Development | 4 | 0 | 120 | Done | fixed the busyness ML orchestration and heuristic match algorithms
2026-07-28 | Sprint 5 | Web Frontend Lead | Final in-person team meeting/bug hunting session | Bug Fix | 9 | 0 | 270 | Done | Final team session to ensure demo would work well. Took MUCH longer than expected
2026-07-28 | Sprint 5 | Backend Lead | 9. PostgreSQL schema, seed data and Redis cache | Data/ML | 3 | 0 | 90 | Done | expanded the real Manhattan restaurant dataset.
2026-07-28 | Sprint 5 | Mobile App Lead | 18. Demo, final paper, presentation and interview prep | Demo/Presentation Prep | 2 | 0 | 60 | Done | prepare demo presentation, flow, and rehearse
2026-08-03 | Final Submission | Scrum Master & Integration Lead | 18. Demo, final paper, presentation and interview prep | Documentation | 4 | 0 | 120 | Done | Revised the IEEE paper with measured busyness-model results replacing placeholders; added runtime architecture diagrams to the GCP, AWS and Azure deployment READMEs.
2026-08-03 | Final Submission | Data & ML Lead | 18. Demo, final paper, presentation and interview prep | Documentation | 3.5 | 0 | 105 | Done | Documented data sources, feature definitions, model evaluation results and limitations for the final IEEE paper and project handover.
2026-08-03 | Final Submission | Mobile App Lead | 18. Demo, final paper, presentation and interview prep | Documentation | 5 | 0 | 150 | Done | Formalise the literature review, collection and summary of preliminary research + identification of new sources
2026-08-04 | Final Submission | Backend Lead | 15. EDI/accessibility features and usability testing | Development | 5 | 0 | 150 | Done | enforced accessibility requirements across SQL, gateway, ML fallback and tests.
2026-08-04 | Final Submission | Scrum Master & Integration Lead | 18. Demo, final paper, presentation and interview prep | Documentation | 5 | 0 | 150 | Done | Built the Manhattan busyness figure notebook for Section IV-G: ran the deployed pipeline over 300 spatially spread venues at 08:00/14:00/20:00, drew the three-panel map from the TLC shapefile, and wrote the accompanying section. Maintained the risk register.
2026-08-04 | Final Submission | Mobile App Lead | 18. Demo, final paper, presentation and interview prep | Documentation | 7 | 0 | 210 | Done | Organising paper restructuring, copy edit of paper, writing formal literature review and re-ordering methodology/ Organising review meeting and action items.
2026-08-05 | Final Submission | Mobile App Lead | 18. Demo, final paper, presentation and interview prep | Documentation | 5 | 0 | 150 | Done | Final copy edit of lit review, writing introduction, refining methodolog (frontend, user testing, and copy edits). Organising review meeting and action items.
2026-08-06 | Final Submission | Mobile App Lead | 18. Demo, final paper, presentation and interview prep | Documentation | 3 | 0 | 90 | Done | Refining introduction and methodology, organising review meeting and action items.
2026-08-07 | Final Submission | Mobile App Lead | 18. Demo, final paper, presentation and interview prep | Documentation | 4 | 0 | 120 | Done | Updating evaluation and results & conclusion, reformatting document, cutting excess to fit within pg requirement.
2026-08-06 | Final Submission | Mobile App Lead | Else / Unmapped | Development | 3 | 0 | 90 | Done | Dockerising the application
2026-08-06 | Final Submission | Scrum Master & Integration Lead | Else / Unmapped | Development | 3 | 0 | 90 | Done | Dockerising the application

## Budget Plan
Budget Task | Owner Role | Primary Sprint | Planned Hrs | Planned Cost | Service Cost | Actual Hrs | Actual Cost | Variance Hrs | % Used | Status | Mitigation / Decision
1. Product discovery, interviews & persona synthesis | Product & UX Lead | Intro | 33.6 | 1008 | 0 | 5 | 150 | -28.6 | 14.88% | On Track
2. Requirements, user stories & backlog management | Product & UX Lead | Sprint 1 | 31.2 | 936 | 0 | 36.5 | 1095 | 5.3 | 117% | Over Plan
3. Competitive analysis & business plan refinement | Product & UX Lead | Sprint 1 | 21.6 | 648 | 0 | 13.5 | 405 | -8.1 | 62.5% | On Track
4. UX flows, wireframes & Google Stitch prototype | Product & UX Lead | Sprint 2 | 45.6 | 1368 | 0 | 24.5 | 735 | -21.1 | 53.73% | On Track
5. Dataset acquisition, EDA & data-quality checks | Data & ML Lead | Sprint 1 | 50.4 | 1512 | 0 | 16 | 480 | -34.4 | 31.75% | On Track
6. Data cleaning, feature engineering & merging | Data & ML Lead | Sprint 2 | 57.6 | 1728 | 0 | 23.5 | 705 | -34.1 | 40.8% | On Track
7. ML / heuristic matching and busyness prediction | Data & ML Lead | Sprint 3 | 66 | 1980 | 0 | 27.5 | 825 | -38.5 | 41.67% | On Track
8. Backend API gateway, booking and offer services | Backend Lead | Sprint 3 | 69.6 | 2088 | 0 | 97 | 2910 | 27.4 | 139.4% | Over Plan
9. PostgreSQL schema, seed data and Redis cache | Backend Lead | Sprint 2 | 42 | 1345 | 85 | 28 | 840 | -14 | 66.67% | On Track
10. Web app implementation: discovery, booking, offers | Web Frontend Lead | Sprint 3 | 66 | 1980 | 0 | 30 | 900 | -36 | 45.45% | On Track
11. Mobile app implementation: onboarding and booking | Mobile App Lead | Sprint 3 | 69.6 | 2088 | 0 | 70.5 | 2115 | 0.9 | 101.3% | Over Plan
12. Restaurant dashboard and campaign workflow | Web Frontend Lead | Sprint 4 | 45.6 | 1368 | 0 | 7 | 210 | -38.6 | 15.35% | On Track
13. Google Maps ETA and geospatial filtering | Backend Lead | Sprint 3 | 33.6 | 1083 | 75 | 14.5 | 435 | -19.1 | 43.15% | On Track
14. Generative AI Dining Copilot integration | Backend Lead | Sprint 4 | 26.4 | 852 | 60 | 0 | 0 | -26.4 | 0% | On Track
15. EDI/accessibility features and usability testing | Product & UX Lead | Sprint 4 | 33.6 | 1008 | 0 | 29 | 870 | -4.6 | 86.31% | On Track
16. Automated tests, integration QA and bug fixing | Scrum Master & Integration Lead | Sprint 4 | 62.4 | 1872 | 0 | 2 | 60 | -60.4 | 3.205% | On Track
17. Cloud deployment, CI/CD and monitoring | Scrum Master & Integration Lead | Sprint 5 | 33.6 | 1103 | 95 | 25 | 750 | -8.6 | 74.4% | On Track
18. Demo, final paper, presentation and interview prep | Product & UX Lead | Sprint 5 | 75.6 | 2268 | 0 | 45 | 1350 | -30.6 | 59.52% | On Track
TOTAL |  |  | 864 | 26235 | 315 | 494.5 | 14835 | -369.5 | 57.23% | On Track
Note: The “owner role” and “planned hours” columns are for reference only (in practice, multiple leads may be assigned to a single task); actual work conditions take precedence.

## Sprint Summary
Sprint | Start | End | Purpose | Planned Hrs | Actual Hrs | Variance Hrs | % Used | Planned Cost | Actual Cost | Status | Review Notes
Intro | 2026-05-18 | 2026-05-22 | Idea, business plan, team contract | 33.6 | 10 | -23.6 | 29.76% | 1008 | 300 | On Track
Sprint 1 | 2026-05-25 | 2026-06-05 | Exploration, user stories, mockups, tech selection | 103.2 | 77 | -26.2 | 74.61% | 3096 | 2310 | On Track
Sprint 2 | 2026-06-08 | 2026-06-19 | Basic apps, basic data analytics, Product & UX presentation | 145.2 | 82.5 | -62.7 | 56.82% | 4441 | 2475 | On Track
Sprint 3 | 2026-06-22 | 2026-07-03 | Connected MVP integration | 304.8 | 126.5 | -178.3 | 41.5% | 9219 | 3795 | On Track
Sprint 4 | 2026-07-06 | 2026-07-17 | Additional features, integration testing, usability testing | 168 | 105.5 | -62.5 | 62.8% | 5100 | 3165 | On Track
Sprint 5 | 2026-07-20 | 2026-07-31 | Polish, public demo, interviews, paper drafting | 109.2 | 95.5 | -13.7 | 87.45% | 3371 | 2865 | On Track
Final Submission | 2026-08-01 | 2026-08-07 | Group paper, repository and backlog submission | 0 | 47.5 | 47.5 |  | 0 | 1425 | Over Plan
TOTAL |  |  |  | 864 | 544.5 | -319.5 | 63.02% | 26235 | 16335 | On Track

## Role Summary
Role | Planned Hrs | Actual Hrs | Variance Hrs | % Used | Actual Cost | Status | Comment
Product & UX Lead | 144 | 57.5 | -86.5 | 39.93% | 1725 | On Track
Scrum Master & Integration Lead | 144 | 67 | -77 | 46.53% | 2010 | On Track | Charges were being incurred for GCP usage.
Data & ML Lead | 144 | 39 | -105 | 27.08% | 1170 | On Track | explore relavant open data source and api, fundamental database design
Backend Lead | 144 | 158 | 14 | 109.7% | 4740 | Over Plan
Web Frontend Lead | 144 | 65 | -79 | 45.14% | 1950 | On Track
Mobile App Lead | 144 | 158 | 14 | 109.7% | 4740 | Over Plan
Note: Allocate planned time evenly among each role based on the total time of 864 hours. (864 / 6 = 144)

## README
How to Use This Tracker
Designed for COMP47360 Product & UX Lead budget updates
Daily input | Only fill the Daily Timesheet sheet.
Required fields | Date, Role, Budget Task, Activity, Hours, Service Cost, Status, Notes / Evidence.
Dropdowns | Role, Budget Task, Activity and Status use dropdown menus from a hidden Lists sheet.
Automatic fields | Sprint is calculated from Date. Actual Cost is calculated as Hours x €30/hr + Service Cost.
Sprint Review | Use Dashboard, Sprint Summary, Budget Plan and Role Summary to explain budget status.
Budget source | Planned hours and service costs come from the revised Business Plan budget section.

## Lists
Roles | Activities | Statuses | BudgetTasks | Sprints
Product & UX Lead | Research | Not Started | 1. Product discovery, interviews & persona synthesis | Intro
Scrum Master & Integration Lead | Requirements | In Progress | 2. Requirements, user stories & backlog management | Sprint 1
Data & ML Lead | UX/UI Design | Blocked | 3. Competitive analysis & business plan refinement | Sprint 2
Backend Lead | Development | Done | 4. UX flows, wireframes & Google Stitch prototype | Sprint 3
Web Frontend Lead | Data/ML |  | 5. Dataset acquisition, EDA & data-quality checks | Sprint 4
Mobile App Lead | Testing/QA |  | 6. Data cleaning, feature engineering & merging | Sprint 5
| Integration |  | 7. ML / heuristic matching and busyness prediction | Final Submission
| Documentation |  | 8. Backend API gateway, booking and offer services
| Meeting |  | 9. PostgreSQL schema, seed data and Redis cache
| Demo/Presentation Prep |  | 10. Web app implementation: discovery, booking, offers
| Deployment |  | 11. Mobile app implementation: onboarding and booking
| Bug Fix |  | 12. Restaurant dashboard and campaign workflow
| Else / Unmapped |  | 13. Google Maps ETA and geospatial filtering
14. Generative AI Dining Copilot integration
15. EDI/accessibility features and usability testing
16. Automated tests, integration QA and bug fixing
17. Cloud deployment, CI/CD and monitoring
18. Demo, final paper, presentation and interview prep
Else / Unmapped